# DATA REVIEW PLAN (DRP/DVP)

Study: IMMUNO-MEL-201 Phase II Melanoma Immunotherapy Trial
Document No.: DRP-IMM201-001
Version: 1.0
Status: Portfolio Example

# Revision History

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0 | 2026-08-01 | Ishita Bansal (Portfolio) | Initial version |

# 1. Purpose

Describe the strategy for ongoing clinical data review, discrepancy identification, query management, and database readiness prior to database lock.

# 2. Study Overview

Longitudinal Phase II oncology study managed in REDCap with Screening, Baseline, Week 4, Week 8, Week 12, Week 18, Week 24, End of Treatment and Safety Follow-up events.

# 3. Scope

Applies to all participant-level clinical data including demographics, eligibility, laboratory, treatment, adverse events, concomitant medications, tumor assessments and protocol deviations.

# 4. Roles and Responsibilities

Clinical Data Manager: perform review and queries.

Clinical Research Coordinator: resolve queries.

Principal Investigator: confirm medical decisions.

Medical Monitor: review SAEs.

Biostatistician: review analysis readiness.

# 5. Critical Data Review Matrix

| Category | Critical Variables | Frequency | Owner | Priority |
| --- | --- | --- | --- | --- |
| Consent | Consent Obtained, Consent Date | Daily | CDM | High |
| Eligibility | Inclusion/Exclusion, Final Eligibility | Daily | CDM/PI | High |
| Randomization | Randomization Number, Arm | Daily | CDM | High |
| Laboratory | ANC, WBC, Platelets, ALT, AST, Creatinine | Weekly | CDM | Medium |
| Safety | AE, SAE, Grade, Outcome | Weekly | CDM/Medical Monitor | High |
| Tumor | RECIST, Target Lesions | Each assessment | CDM | High |
| Protocol | Deviations | Weekly | CDM | Medium |

# 6. Data Review Workflow

Run built-in REDCap Data Quality rules.

Execute custom edit checks.

Review Enrollment, Laboratory, Safety and Tumor listings.

Document findings in Query Tracker.

Issue queries to site.

Review responses.

Close verified queries.

Repeat until database is clean.

# 7. Edit Check Summary

| ID | Description |
| --- | --- |
| EC001 | Consent Date required when Consent Obtained = Yes |
| EC002 | Randomization only if Eligible |
| EC003 | Treatment Date on/after Consent Date |
| EC004 | Lab values only when Sample Collected = Yes |
| EC005 | AE End Date on/after AE Start Date |
| EC006 | ConMed End Date on/after Start Date |
| EC007 | Pregnancy testing when applicable |
| EC008 | RECIST response after assessment |
| EC009 | Visit dates within window |
| EC010 | No randomization for screen failures |

# 8. Review Listings

Enrollment

Consent

Eligibility

Medical History

Laboratory

Vital Signs

Treatment

Adverse Events

Concomitant Medications

Tumor Assessment

Protocol Deviations

End of Treatment

Safety Follow-up

Open Queries

Missing Data

# 9. Query Management

Priority definitions:

| Priority | Examples | Target |
| --- | --- | --- |
| High | Consent, Eligibility, SAE | 24–48 h |
| Medium | Labs, dates | 5 business days |
| Low | Administrative | 10 business days |

# 10. KPIs

Open queries

Average query age

Missing data %

Visit completion

Screen failure rate

SAE count

Protocol deviations

RECIST distribution

# 11. Database Lock Checklist

☐ All queries closed

☐ Eligibility verified

☐ Randomization reconciled

☐ Laboratory review complete

☐ SAEs reconciled

☐ Protocol deviations finalized

☐ RECIST complete

☐ Missing data reviewed

☐ Approval for database lock

# 12. Portfolio Evidence

Attach REDCap screenshots, Data Quality outputs, Query Tracker, SQL examples and Power BI dashboards.